## Test summary report
Tester | TDHPhuoc, HTPhuc, TQViet, TDBinh
Date | 17/08/2024
ID | Feature Name | Description | Number of test case failed | Number of test case passed
UC01 | Register | allow user to register account | 1 | 4
UC02 | Login | allow user to login with registered account | 0 | 5
UC03 | Reset Password | allow user to reset password when they lost it | 0 | 4
UC04 | Assign Admin | allow user with admin role can assign other user role to admin | 0 | 4
UC05 | Signout | allow user to signout current session | 2 | 2
UC06 | Add product to cart | alow user to add a product to their cart | 0 | 4
UC07 | Change item amount in Cart | allow user to change item amount in their carts | 0 | 3
UC08 | Remove Item | Allows a user to remove a product from their shopping cart. | 0 | 2
UC09 | View Product Details | Allows a user to view detailed information about a product. | 0 | 3
UC10 | Search Product | Allows a user to search for specific products on the Justatea platform. | 0 | 4
UC11 | Filter Product | Allows a user to filter product search results based on specific criteria. | 0 | 5
UC12 | Sort Product | Allows a user to sort product listings based on various criteria (e.g., price, popularity). | 0 | 3
UC13 | Customize Order | Allows a user to customize options for a product in their shopping cart (e.g., size, toppings). | 0 | 5
UC14 | View Product Reviews | Allows a user to view customer reviews and ratings for a product. | 0 | 4
UC15 | View Featured Products | allows users to discover and access curated lists of best-selling, top-rated, and newly added products on the Justatea e-commerce website. | 0 | 3
UC16 | Leave Reviews | use case allows a user to provide feedback and ratings for products they have purchased on the Justatea e-commerce website. | 1 | 4
UC17 | Enter Contact Information | use case allows a user to provide their contact details during the checkout process on the Justatea e-commerce website. | 1 | 4
UC18 | Apply Voucher | use case allows a user to enter and apply a voucher code during the checkout process to receive a discount on their order. | 1 | 4
UC19 | Payment Method | use case allows a user to select and enter payment information during the checkout process. | 0 | 5
UC20 | Place Order | use case allows a user to finalize their purchase and submit their order for processing. | 1 | 4
UC21 | Add New Products | use case allows vendors or administrators to add new food and beverage products to the Justatea e-commerce platform. | 1 | 4
UC23 | Manage Users | The Manage Users use case involves the management of user accounts and profiles on the Justatea e-commerce platform | 1 | 4
UC24 | View Order as Admin | The View Orders use case involves the capability to view and manage customer orders on the Justatea e-commerce platform | 0 | 5
UC25 | Account settings | This use case involves customers accessing and modifying their account settings within the Justatea e-commerce platform to manage personal information and preferences. | 2 | 3
UC26 | Customer Support using LLMS | It provides automated responses, real-time assistance, and handles customer queries efficiently. | 3 | 2
UC29 | Updating information for LLMs chatbot | Involves updating and maintaining information within the Learning Management System (LLMS) chatbot used for customer support on the Justatea platform. | 0 | 5

## Bug report
Defect ID | Defect Title | Defect Description | Function ID | Severity | Reported By | Date Reported | Status | Comment
BUC16UI05 | Cannot save partially completed review | The blanks commented by users do not save previous partially completed comment | UC16 | Low | TDHPhuoc | 2024-08-17 | Open
BUC17UI04 | Cannot check valid contact information field submission | The system allows users to enter invalid format fields. | UC17 | Low | TDHPhuoc | 2024-08-17 | Open
BUC18UI05 | The vouchers are overwritten | When applying voucher001, the products price will reduce by 10%. After that applying voucher002, due to its expiry date, the system cannot apply voucher002, and this causes the voucher001 not working (overwritten). | UC18 | Medium | TDHPhuoc | 2024-08-17 | Open
[5 empty] | TDHPhuoc | 2024-08-17 | Open
BUC20UI05 | Cancellation of Pending Order Before Momo Payment | The order will not be removed when cancelling payment progress in Momo pages, it will be existed forever without dealing with them more. It causes the watse of memory of database. | UC20 | Low | TDHPhuoc | 2024-08-17 | Open
BUC21UI04 | Addition of New Product with Unsupported File Formats | The system allows to upload other file types (.xls, .exe) in image field of Add New Products usecase. This makes the showcase of products cannot work correctly. | UC21 | High | TDHPhuoc | 2024-08-17 | Open
BUC1UI03 | Allow invalid email format in register account | User can register their account even with invalid email format | UC01 | High | TQViet | 2024-08-17 | Open
BUC5UI03 | Cannot Sign Out from Multiple Sessions | User can only signout from their current session but not every sessions on different devices or platforms. | UC05 | High | TQViet | 2024-08-17 | Open
BUC5UI04 | User can access to previous page after signout | After signout, user still able to access to previous page when they still sign in. | UC05 | Medium | TQViet | 2024-08-17 | Open
BUC23UI05 | Fail Synchronization Between Firebase Authentication and Firestore | After delete user in authentication, user's document is not deleted | UC23 | Low | TDBinh | 2024-08-17 | Open
BUC25UI03 | No data shema when updating user's phone | After enter invalid phone number format with a full string, the system still accepted the new value and update it | UC25 | Medium | TDBinh | 2024-08-17 | Open
BUC25UI05 | Upload invalid profile picture format | After choosing a file for profile picture that not in form of png, jpg,... Program still accept and the picture is not displayed on profile | UC25 | Medium | TDBinh | 2024-08-17 | Open
BUC26UI01 | Chat bot faill to response when ask about store hours | After ask "what is store hours" the chat bot response with: I'm sorry, but I can only provide information about our products based on the information provided. The store hours are not included in the data. | UC26 | Medium | TDBinh | 2024-08-17 | Open
BUC26UI03 | Chat bot fail to response when ask about current promotions | After ask "what current voucher " the chat bot response with: I'm sorry, but I don't have access to information regarding current vouchers. | UC26 | Medium | TDBinh | 2024-08-17 | Open
BUC26UI05 | Chat bot fail to response when ask about members of the shop | After ask "who are the members of the shop " the chat bot response with: I'm sorry, but I only have access to product information for JustaTea. The information about the members of the shop is not available.. | UC26 | Medium | TDBinh | 2024-08-17 | Open
Note on D1: ====== ID#AAABCvoFu_I Vu V. Nguyen (2023-12-20 06:51:13) Function ID of the function where the defect is found
Note on E1: ====== ID#AAABCvoFu_A Vu V. Nguyen (2023-12-20 06:51:13) High, Medium, or Low
Note on F1: ====== ID#AAABCvoFu_E Vu V. Nguyen (2023-12-20 06:51:13) Name of the tester who reports the defect
Note on H1: ====== ID#AAABCvoFu-8 Vu V. Nguyen (2023-12-20 06:51:13) Open or Closed